I2U2 Jan 7th  - 8th Meeting Notes

MB:  Understanding requirements of new grant is our central focus

We need to leave with a clear plan--who, what, when--to accomplish this

Special Topics suggestions:

1.  e-Lab requirements

MB:  the "basic, standard e-Lab" needs to be stood up in time to fulfill evaluation requirements

(introductions done; Liz introduced Phong as new IT developer;  lives near UC at Hyde Park, will work with Mihael and Mike at UC most of the time, though employed at FNAL)

Review of "Requirements" document, partially reprinted here:

e-Labs must:

Use authentic data for scientific investigations that students design.

Have common components [http://www13.i2u2.org/glossary/index.php/E-Lab_Outline]:

Project Page – general overview

Teacher Pages – common required format and information

Student Pages – common navigation and required sections with open design

Support collaborative learning.

Support common learner outcomes in addition to specific e-Lab content LOs.

Require only a browser for school-based users.

--comment in discussion:  other items may be integrated into the browser-only format...

Have capabilities for data access, processing and publishing and for reporting results (and some for data upload).

Have grid-based analysis code and administrative tools based on the SWIFT infrastructure.

Have searchable metadata associated with data and data products (plots, posters).

Use virtual data tools and techniques.

Use common infrastructure for educational scaffolding (milestones, logbook, references).

Support a virtual community of learners with online discussion forums, document storage, wiki-like interactive publishing and help desks.

Offer professional development workshops to help teachers become effective users.

--Tom L, Dale, Tom J, Bob P must get together to assemble the content of these workshops.  We (I2U2 this funding round) are evaluating e-Labs as used by teachers who have been through workshops)

Review of requirements

| Cosmic | LIGO | CMS | i-Lab | e-Lab Requriements |
| --- | --- | --- | --- | --- |
| x | x | x | x | Use authentic data for scientific investigations that students design. |
| / | / | / | NA | Have common components [http://www13.i2u2.org/glossary/index.php/E-Lab_Outline]: |
| x | x | x | NA | Project Page – general overview |
| x | x | / |  | Teacher Pages – common required format and information |
| x | x | / | NA | Student Pages – common navigation and required sections with open design |
| x | x | / | x | Support collaborative learning. |
| / | / | / | / | Support common learner outcomes in addition to specific e-Lab content LOs. |
| X | X | x | x | Require only a browser for school-based users. |
| x | / | / | / | Have capabilities for data access, processing and publishing and for reporting results (and some for data upload). |
| ? | ? | ? |  | Have grid-based analysis code and administrative tools based on the SWIFT infrastructure. |
| x | / | / |  | Have searchable metadata associated with data and data products (plots, posters). |
| ? | ? | ? |  | Use virtual data tools and techniques. |
| x | x | / |  | Use common infrastructure for educational scaffolding (milestones, logbook, references). |
| / | / | / |  | Support a virtual community of learners with online discussion forums, document storage, wiki-like interactive publishing and help desks. |
| x | x |  |  | Offer professional development workshops to help teachers become effective users. |

Mark S on what it is to be an i-Lab: an informal experience which meets some of those requirements, with an on-line follow-up enabling full investigation sans teacher. (Investigations with Cosmic using QN/Walta cards, plus richer (flux, temp, pressure, altitude) data set from balloon flights, are under development.)

--What does it mean to "have grid-based analysis code..."?  Run on multiple nodes in a "grid" context?

Various levels of questioning:  how is the grid exposed to the user?  Is there a common interface?  Is the implementation strategy (the details of how the grid is accessed) the same?  Need it be?

Mike W:  focus on getting some useage where students can see the ability, and exercise it, to run bigger jobs.  Nothing fancy:  students can run bigger things--that's what the grid should mean to them.  We should be able to measure and document that students are doing that.  Eric:  need to be able to check on a running job....Mike agreed.  The focus:  what does the grid-based requirement mean to the end user?

1.  students should be aware of the computing resource needs of their requests

2.  students should be confronted with execution choices

3.  students should be confronted with the implications of the choices they make (where the job is running, its status, where it is running

4.  students should be able to intervene to kill bad execution choices

5.  should be see some blocking mechanisms protecting against bad choices

MW:  "science first, grid second";  "collaborative analysis of sci data is primary;  secondarily, highlighting the importance of HPC in supporting scientific analysis is secondary but also a legitimate goal"

We considered this possible replacement tech LO:  students will know and be able to formulate questions that require higher performance computational analysis tools,

We tentatively agreed instead on this LO:  students can explain their choices from among a range of computational analysis tools, justifying the cost of their choices

11AM:  moved to evaluation requirements:  here's the relevant sections from the "requirements" document:

I2U2 Requirements 2008 - 2012

Project Goal: To address these research questions:

Do students learn science practices through e-Lab—grid-enabled virtual investigations?

Specifically, do they increase their skills in using technology as a tool for conducting science (skills that mirror real-world science)?

Do they engage in scientific collaboration and increase their knowledge of related science and grid concepts?

Does the Interactions in Understanding the Universe virtual learning community support teacher practices and development to enable students to learn science practices with the I2U2 cyber-enabled tools?

Introduction: The current I2U2 NSF grant (written for the DR-K12 program: http://www.nsf.gov/funding/pgm_summ.jsp?pims_id=500047) has a tight research focus on testing three e-Labs and the i-Lab. Given the NSF direction on rigorous research, providing data per the evaluation plan is vital to the success of the grant and the future of e-Labs as a model for teaching and learning science using cyber technology. Everyone in the collaboration must be involved.

Deliverables: 4 production e/i-Labs including virtual learning community tools and evaluation tools, data and reports.

Time Line: COSMIC AND LIGO PRODUCTION e-LABS MUST HAVE COMPLETED PRODUCT DEVELOPMENT EVALUATION (see below) BY JUNE 1, 2009 AND CMS AND THE COSMIC i-LAB BY JUNE 1, 2010. This includes tools for the virtual learning community and pre- post-tests.

Year 1 Test

Prior to Summer 2009 – Complete product development phase (see below) for Cosmic and LIGO.

Summer 2009 – Cosmic and LIGO professional development workshops for 10 teachers each

Academic year 2009-2010 – Classroom implementation phase including community building & support

September 30 – Year 1 evaluation report

Year 2 Test

Prior to Summer 2010 – Complete product development phase (see below) for CMS and Cosmic i-Lab

Summer 2010 – Cosmic, LIGO and CMS professional development workshops as for 10 teachers each

Academic year 2010-2011 – Classroom implementation phase including community building & support

June 1 – May 30 – Cosmic i-Lab implementation at Adler

September 30 – Year 1 evaluation report

Year 3 Test

Summer 2011 – Cosmic, LIGO and CMS professional development workshops for 10 teachers each

Academic year 2011-2012 – Classroom implementation phase including community building & suppor.

June 1 – May 30 – Cosmic i-Lab implementation at Adler

September 30 – Year 1 evaluation report

Evaluation Plan Components:

Product Development Phase for e/i-Labs

Think aloud

Expert review

Beta Test

Small scale beta test

Production scale beta test

In addition, the e-Lab specific pre- post-tests must be validated through use by some 100 students.

Implementation Phase (Ongoing Assessment for e-Labs)

Learner objective achievement

Pre- post-tests

Posters/rubrics

Personal logs

Workshops and follow up support for teachers

Surveys & phone interviews

Help desk reports

Online community

Review on comments & phone interviews

MB:  we may not be able to implement every (technically-complex) change in one year, from those suggested during TAP and Expert Review.

Elizabeth:  we'll need input on which sorts of requested changes ARE technically more complicated to implement

MB:  we need the support elements in place, along side of the e-Labs;  both move forward together...

Year 2 may bring a new round of changes in both the e-Lab and the support tools...

Teachers get support:  stipends and travel, for participation in workshops, who are the 10 teachers each year who implement the e-Labs

Detailed examination of each of the steps: (from beginning on Page 4 of the Evaluation Tool Kit:

JY: Questions for pre and post tests need to be done by june;  cosmic is in hand;  LIGO isn't yet.  Also, should technology LO Qs be added to the test.  We'll deliver an answer by the end of this 2-day meeting...

May need some examination of HPC vs grid language throughout the evaluation document...

Bob will check on whether the post-WS form in the Eval ToolKit is the same as the one he uses (p. 30, 31...)

Elizabeth:  we can use screencasting to capture the raw interaction, but then should extract the essential data from that raw data and send that to evaluators

The TAP should take an hour;  it should cover the whole e-Lab but only in a representative sort of way;  the person should be someone already reasonably familiar with science and e-Lab content...

Small-scale testing, beginning with a small number of high-end students:  if they can't do it, no one can...then move to large scale,

Lucy raised the question of whether this procedure leaves out input from a broader range of students at the most formative stage of development....a robust discussion ensued:)

Dale:  LIGO experience is with diverse, lower-end, younger users

Karen:  doesn't that just push the confounding variables down the road just a bit?

Clarification of numbers involved:  10 - 15 students, total, for small scale beta; 10-15 CLASSROOMS for large scale beta testing

So cosmic is under pressure to do small and as large a scale testing as possible, before the summer, so that the common LOs and Cosmic content LOs will have test Qs validated.

After some discussion, scantron/paper copies of testing THIS SPRING seems the way to go, rather than to adjust the cosmic database....