## Sheet1
|  | January |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | Sept 09 - May 10
|  | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31
COSMIC
2.4.10 | [H] Articulate common teacher workshop goals | bar: January 19 to March 2
2.4.1 | [H] Design and implement a data blessing approach | bar: January 19 to May 25
2.4.4 | [H] Clean up bug issues | bar: January 19 to March 9
2.4.7 | [L] Implement Widecard datasearches | bar: January 19 to February 23
2.6.3 | [M] Copy Help Desk e-mail to Help Desk Forum | bar: January 19 to February 16
2.6.4 | [L] Create a statistics/reporting tool (Bug #140) | bar: January 19 to February 9
2.4.3 | [H] Adjust execution controls and results pages to meet technology LO. | bar: January 26 to March 9
2.4.6 | [H] Complete and respond to TAPs | bar: January 26 to February 2; February 16 to February 23; April 6 to April 13
2.4.13 | [H] Update tutorial screen grabs | bar: February 16 to March 9; June 15 to August 17
2.5.1 | [H] Add learning community link to teacher pages | bar: February 23 to March 9
2.4.9 | [H] Complete peer (expert) review | bar: March 2 to March 16
2.4.12 | [L] Implement progress bar for data uploads... | bar: March 9
2.4.5 | [H] Create test suite | bar: April 6 to April 20
2.4.8 | [H] Complete beta test (small scale, large scale) | bar: January 26 to February 2; March 16 to June 8
2.4.2 | [H] Validate the pre and post tests | bar: January 26 to June 8
2.4.11 | [H] Run Workshops | bar: June 15 to August 17
LIGO
2.3.14 | [H] Articulate common teacher workshop goals | bar: January 19 to March 2
2.3.9 | [H] Get Bluestone server running at ANL | bar: January 19 to February 23
2.3.3. | [H] Clean up LO and milestone issues | bar: January 26 to March 9
2.3.7 | [H] Get DMTROOT running on teraport | bar: February 2 to March 9
2.3.2 | [H] Develop interface for Bluestone to run analyses via Swift | bar: February 9 to February 16
2.3.5 | [H] Implement saving Bluestone-specific metadata to e-Lab (PHONG?) | bar: February 9 to February 23
2.3.8 | [H] Enable rerunning analysis using metadata associated with plot | bar: February 23
2.5.1 | [H] Add learning community link to teacher pages | bar: February 23 to March 9
2.3.1 | [H] Formulate and implement pre and post test questions | bar: February 23 to March 16
2.3.16 | [H] Update tutorials | bar: February 23 to March 2; June 15 to August 17
2.3.12 | [H] Complete and respond to TAPs | bar: March 9 to March 16
2.3.13 | [H] Complete peer review | bar: March 23 to March 30
2.5.1 | [H] Integrate Forum/Wiki and e-Lab User databases | bar: January 19 to February 23
2.3.10 | [M] Establish access to data at Caltech | bar: January 19 to February 23
2.3.11 | [L] Continue to implement run time estimates and actual values | January 19: Floater
2.5.2 | [L] Redesign web portal to support web portal for teachers... | January 19: Floater
2.3.6 | [H] Complete beta test (small scale, large scale) | bar: April 6 to May 25
2.3.4 | [H] Validate LIGO pre and post tests | bar: June 1 to June 8
2.3.15 | [H] Run Workshops | bar: June 15 to August 17
CMS
2.2.4 | Articulate common workshop goals | bar: January 19 to March 2
2.2.6 | Obtain MC data | bar: January 19 to March 9
2.2.8 | Run MC Studies | bar: March 9 to March 16
2.2.9 | Integrate teacher & student pages | bar: March 23 to March 30
2.2.10 | Integrate multilevel investigations | bar: January 19; March 23 to March 30
2.5.1 | Add learning community link to teacher pages | bar: March 30 to April 6
2.2.5 | Develop CMS pre- post test questions | bar: April 6 to April 13
2.1.2 | Complete & respond to Think Aloud | bar: April 6 to April 13
2.2.3 | Complete & resond to peer review | bar: April 20 to April 27
2.2.1 | Enable OGRE to run analyses with Swift | bar: February 2 to March 30
2.2.11 | Integrate into existing database | bar: February 2 to March 30
2.2.13 | Beta testing on CMS dime | bar: May 18 to May 25
2.2.14 | Run workshops | bar: June 22 to August 17
2.2.12 | Complete beta test | [33 empty] | -
2.1.7 | Validate CMS pre- post-test | [33 empty] | -
I-Lab
2.1.3 | [H] Evaluation: coordinate with Jean for i-Lab | bar: January 26 to July 20
2.1.2 | [H] Deploy exhibit | bar: February 2 to April 27
2.1.4 | [H] Create user pages | bar: March 2 to March 30
2.1.3 | [H] Investigate how i-Lab hooks into e-Lab | bar: April 20 to August 3
2.1.5 | [M] Develops/study follow up rates from exhibit to web (card dispenser) | bar: May 25 to July 13
Common
2.6.2 | [L] Establish a mirror site independent of Argonn | January 19: Floater
Grid
2.7.1 | [M] Parallelization of Cosmic workflow for Swift | bar: February 2 to March 2
2.7.2 | [H] Performance metrics and estimates...
2.7.3 | L] Enable elabs to work on multiple sites...
F |  | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31
|  | 19: January; 2: February; 2: March; 6: April; 4: May; 1: June; 6: July; 3: August | Sept 09 - May 10
Main effort | bar: 19
Ongoing but minimal effort in a given week | bar: 19
Done