## Sheet1
|  | January |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September to May
|  | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31
2.2.1 | Integrate teacher & student pages | bar: February 16 to February 23
2.2.2 | Enable OGRE to run analyses with Swift | bar: February 2 to March 30
2.2.3 | Complete beta test | [33 empty] | X
2.2.4 | Integrate multilevel investigations | bar: February 16 to February 23
2.2.5 | Integrate exisiting database | bar: February 2 to March 30
2.2.6 | CMS pre- post test questions developed | bar: March 2 to March 9
2.2.7 | Run workshops | bar: July 13
2.2.8 | Complete & resond to peer review | bar: March 16 to March 23
2.2.9 | Articulate common workshop goals | bar: January 19
2.2.10 | Beta testing on CMS dime | bar: May 18 to May 25
2.2.11 | Obtain MC data | bar: January 19 to January 26
2.2.12 | Run MC Studies | bar: February 2 to February 9
2.1.1 | Complete & respond to Think Aloud | bar: March 2 to March 9
2.1.2. | Validate CMS pre- post-test | [33 empty] | X
2.1.3 | Add learning community link to teacher pages | bar: February 16 to February 23
Check start date
Not I2U2 beta test -- for CMS deadline
2.2.9 | Articulate common workshop goals | bar: January 19
2.2.11 | Obtain MC data | bar: January 19 to January 26
2.2.12 | Run MC Studies | bar: February 2 to February 9
2.2.1 | Integrate teacher & student pages | bar: February 16 to February 23
2.2.4 | Integrate multilevel investigations | bar: February 16 to February 23
2.1.3 | Add learning community link to teacher pages | bar: February 16 to February 23
2.2.6 | CMS pre- post test questions developed | bar: March 2 to March 9
2.1.1 | Complete & respond to Think Aloud | bar: March 2 to March 9
2.2.8 | Complete & resond to peer review | bar: March 16 to March 23
2.2.2 | Enable OGRE to run analyses with Swift | bar: February 2 to March 30
2.2.5 | Integrate exisiting database | bar: February 2 to March 30
2.2.10 | Beta testing on CMS dime | bar: May 18 to May 25
2.2.7 | Run workshops | bar: July 13
2.2.3 | Complete beta test | [33 empty] | X
2.1.2. | Validate CMS pre- post-test | [33 empty] | X